## Read Me
ShopEase QA Workbook
SIMULATED PROJECT: ShopEase is a fictional application. Nothing in this workbook has been executed yet. Every test case starts as Not Executed.
Sheets
Summary – counts and percentages calculated by formulas. They show Not started until you execute tests.
Test Cases – all 67 manual test cases. Status and Actual Result are read from the Execution Tracker (do not type in them).
Execution Tracker – the ONLY place where you record results. Yellow cells are for you to fill in.
Defect Tracker – 10 SAMPLE defects (Type = SAMPLE, for learning). Add your real defects in the yellow rows below them with Type = ACTUAL.
RTM – requirement to test case to SQL query to expected database state. Execution Status is read from the Execution Tracker.
How to record a result (example of the format; this is NOT a real result)
In Execution Tracker pick Status from the drop-down (Pass / Fail / Blocked / Not Executed), type your name, the date (for example 2026-11-02), what you actually saw, and the Defect ID if the test failed (for example BUG-001).
Example row: TC_REG_02 ¦ Fail ¦ Rishi ¦ 2026-11-02 ¦ System accepted the duplicate email and created a second account ¦ BUG-001
Legend
Yellow cell = you fill it in. White cell = given text or formula. Pass % uses executed tests (Pass + Fail + Blocked) as the base.
SQL query IDs (Q01 to Q48) are in sql/03_validation_queries.sql and explained in docs/sql_query_guide.md.

## Summary
Test Execution Summary
All values are formulas on the Execution Tracker. They show Not started until you execute tests.
Total test cases | 67
Pass | 0
Fail | 0
Blocked | 0
Not Executed | 67
Executed (Pass + Fail + Blocked) | 0
Pass % of executed | Not started
Execution progress % (executed / total) | 0%
Check: counts add up to total | OK
Results by module
Module | Total | Pass | Fail | Blocked | Not Executed
User Registration | 9 | 0 | 0 | 0 | 9
Login and Logout | 7 | 0 | 0 | 0 | 7
Product Search | 4 | 0 | 0 | 0 | 4
Categories and Product Details | 4 | 0 | 0 | 0 | 4
Shopping Cart | 5 | 0 | 0 | 0 | 5
Quantity Updates | 5 | 0 | 0 | 0 | 5
Checkout | 4 | 0 | 0 | 0 | 4
Address Validation | 5 | 0 | 0 | 0 | 5
Order Placement | 4 | 0 | 0 | 0 | 4
Payment Status Simulation | 5 | 0 | 0 | 0 | 5
Order History | 3 | 0 | 0 | 0 | 3
Order Cancellation | 5 | 0 | 0 | 0 | 5
Inventory Validation | 4 | 0 | 0 | 0 | 4
End-to-End | 3 | 0 | 0 | 0 | 3
Results by priority
Priority | Total | Pass | Fail | Blocked | Not Executed
High | 49 | 0 | 0 | 0 | 49
Medium | 17 | 0 | 0 | 0 | 17
Low | 1 | 0 | 0 | 0 | 1
Actual defects (Type = ACTUAL only; samples excluded)
Severity | Total | Open (not Closed, Rejected or Duplicate)
Critical | 0 | 0
High | 0 | 0
Medium | 0 | 0
Low | 0 | 0

## Execution Tracker
TC ID | Module | Priority | Status | Executed By | Execution Date | Actual Result (what you saw) | Defect ID | Remarks
TC_REG_01 | User Registration | High | Not Executed
TC_REG_02 | User Registration | High | Not Executed
TC_REG_03 | User Registration | Medium | Not Executed
TC_REG_04 | User Registration | High | Not Executed
TC_REG_05 | User Registration | High | Not Executed
TC_REG_06 | User Registration | High | Not Executed
TC_REG_07 | User Registration | High | Not Executed
TC_REG_08 | User Registration | Medium | Not Executed
TC_REG_09 | User Registration | High | Not Executed
TC_LOG_01 | Login and Logout | High | Not Executed
TC_LOG_02 | Login and Logout | High | Not Executed
TC_LOG_03 | Login and Logout | Medium | Not Executed
TC_LOG_04 | Login and Logout | Medium | Not Executed
TC_LOG_05 | Login and Logout | High | Not Executed
TC_LOG_06 | Login and Logout | High | Not Executed
TC_LOG_07 | Login and Logout | High | Not Executed
TC_SRC_01 | Product Search | High | Not Executed
TC_SRC_02 | Product Search | Medium | Not Executed
TC_SRC_03 | Product Search | Medium | Not Executed
TC_SRC_04 | Product Search | High | Not Executed
TC_CAT_01 | Categories and Product Details | High | Not Executed
TC_CAT_02 | Categories and Product Details | High | Not Executed
TC_CAT_03 | Categories and Product Details | High | Not Executed
TC_CAT_04 | Categories and Product Details | Medium | Not Executed
TC_CRT_01 | Shopping Cart | High | Not Executed
TC_CRT_02 | Shopping Cart | High | Not Executed
TC_CRT_03 | Shopping Cart | High | Not Executed
TC_CRT_04 | Shopping Cart | Medium | Not Executed
TC_CRT_05 | Shopping Cart | Medium | Not Executed
TC_QTY_01 | Quantity Updates | High | Not Executed
TC_QTY_02 | Quantity Updates | High | Not Executed
TC_QTY_03 | Quantity Updates | High | Not Executed
TC_QTY_04 | Quantity Updates | High | Not Executed
TC_QTY_05 | Quantity Updates | Medium | Not Executed
TC_CHK_01 | Checkout | High | Not Executed
TC_CHK_02 | Checkout | High | Not Executed
TC_CHK_03 | Checkout | High | Not Executed
TC_CHK_04 | Checkout | Medium | Not Executed
TC_ADR_01 | Address Validation | High | Not Executed
TC_ADR_02 | Address Validation | High | Not Executed
TC_ADR_03 | Address Validation | High | Not Executed
TC_ADR_04 | Address Validation | Medium | Not Executed
TC_ADR_05 | Address Validation | High | Not Executed
TC_ORD_01 | Order Placement | High | Not Executed
TC_ORD_02 | Order Placement | High | Not Executed
TC_ORD_03 | Order Placement | Medium | Not Executed
TC_ORD_04 | Order Placement | High | Not Executed
TC_PAY_01 | Payment Status Simulation | High | Not Executed
TC_PAY_02 | Payment Status Simulation | High | Not Executed
TC_PAY_03 | Payment Status Simulation | Medium | Not Executed
TC_PAY_04 | Payment Status Simulation | Medium | Not Executed
TC_PAY_05 | Payment Status Simulation | Medium | Not Executed
TC_HIS_01 | Order History | High | Not Executed
TC_HIS_02 | Order History | High | Not Executed
TC_HIS_03 | Order History | High | Not Executed
TC_CAN_01 | Order Cancellation | High | Not Executed
TC_CAN_02 | Order Cancellation | High | Not Executed
TC_CAN_03 | Order Cancellation | High | Not Executed
TC_CAN_04 | Order Cancellation | High | Not Executed
TC_CAN_05 | Order Cancellation | Low | Not Executed
TC_INV_01 | Inventory Validation | High | Not Executed
TC_INV_02 | Inventory Validation | High | Not Executed
TC_INV_03 | Inventory Validation | High | Not Executed
TC_INV_04 | Inventory Validation | Medium | Not Executed
TC_E2E_01 | End-to-End | High | Not Executed
TC_E2E_02 | End-to-End | High | Not Executed
TC_E2E_03 | End-to-End | High | Not Executed

## Test Cases
TC ID | Module | Test Scenario | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Status | Priority | Test Type
TC_REG_01 | User Registration | Register with valid details | User not logged in; email and phone not registered | First: Anitha, Last: Rao, Email: anitha.rao@example.com, Phone: 9123456780, Password: Pass@1234, Confirm: Pass@1234 | 1. Open Register page 2. Enter the test data 3. Click Register | Account created, success message shown, user redirected to Login. DB: 1 new customers row, status ACTIVE, password stored as hash (SQL Q01) |  | Not Executed | High | Positive
TC_REG_02 | User Registration | Register with an already registered email | ravi.kumar@example.com already exists | Email: ravi.kumar@example.com, Phone: 9123456781, other fields valid | 1. Open Register page 2. Enter data with the existing email 3. Click Register | Error 'Email already registered'; no new customer row (SQL Q02 returns 0 rows) |  | Not Executed | High | Negative
TC_REG_03 | User Registration | Register with an already registered phone number | Phone 9876543210 already exists | Phone: 9876543210, Email: new.user1@example.com, other fields valid | 1. Open Register page 2. Enter data with the existing phone 3. Click Register | Error 'Phone number already registered'; no new row (SQL Q03 returns 0 rows) |  | Not Executed | Medium | Negative
TC_REG_04 | User Registration | Invalid email formats are rejected | Register page open | ravi.kumar@ ; ravi@.com ; ravi kumar@example.com ; ravi.example.com | 1. Enter each invalid email one by one with other valid data 2. Click Register after each | Each attempt shows 'Enter a valid email address'; no account created |  | Not Executed | High | Validation
TC_REG_05 | User Registration | Mandatory fields left blank | Register page open | All fields empty | 1. Click Register without entering anything | Inline error shown for every mandatory field; form not submitted |  | Not Executed | High | Negative
TC_REG_06 | User Registration | Weak passwords are rejected (password policy) | Register page open | abcd1234 (no uppercase/special) ; PASSWORD@1 (no lowercase) ; Password@ (no digit) ; Pass1234 (no special) | 1. Fill valid data and enter one weak password 2. Click Register 3. Repeat for each password | Each is rejected and the message lists the missing rule (BR-02) |  | Not Executed | High | Validation
TC_REG_07 | User Registration | Password length boundary values | Register page open | 7 chars: Pass@12 ; 8 chars: Pass@123 ; 20 chars: Passw@rd123456789012 ; 21 chars: Passw@rd1234567890123 | 1. Enter each password with valid other data 2. Click Register | 7 and 21 characters rejected; 8 and 20 characters accepted (use a unique email each time) |  | Not Executed | High | Boundary
TC_REG_08 | User Registration | Confirm password does not match | Register page open | Password: Pass@1234, Confirm: Pass@12345 | 1. Enter mismatching passwords 2. Click Register | Error 'Passwords do not match'; account not created |  | Not Executed | Medium | Negative
TC_REG_09 | User Registration | Phone number validation | Register page open | 12345 ; 5876543210 (starts with 5) ; 98765abcde ; 98765432101 (11 digits) | 1. Enter each phone value with other valid data 2. Click Register | All rejected; only 10 digits starting 6-9 allowed (BR-01) |  | Not Executed | High | Validation
TC_LOG_01 | Login and Logout | Login with valid credentials | Registered ACTIVE user | ravi.kumar@example.com / Test@1234 | 1. Open Login page 2. Enter email and password 3. Click Login | Login succeeds, home page shows user name. DB: last_login_at updated, failed_login_attempts = 0 |  | Not Executed | High | Positive
TC_LOG_02 | Login and Logout | Login with wrong password | Registered ACTIVE user | ravi.kumar@example.com / Wrong@123 | 1. Enter valid email and wrong password 2. Click Login | Generic message 'Invalid email or password'; not logged in. DB: failed_login_attempts increased by 1 |  | Not Executed | High | Negative
TC_LOG_03 | Login and Logout | Login with unregistered email | None | nobody@example.com / Test@1234 | 1. Enter unregistered email and any password 2. Click Login | Same generic message (does not reveal that the email is unknown) |  | Not Executed | Medium | Negative
TC_LOG_04 | Login and Logout | Login with blank fields | Login page open | Empty email and password | 1. Click Login with both fields empty 2. Enter only email and click Login | Mandatory field messages shown; no login attempt counted |  | Not Executed | Medium | Validation
TC_LOG_05 | Login and Logout | Account locks after 5 wrong passwords (boundary 4 vs 5) | Use a fresh ACTIVE user with 0 failed attempts | priya.nair@example.com wrong password Bad@1234 | 1. Reset failed_login_attempts to 0 using SQL 2. Enter wrong password 4 times; check message and DB 3. Enter wrong password a 5th time 4. Now enter the correct password Test@1234 | After 4 attempts the account is still usable; after the 5th the status becomes BLOCKED and even the correct password is rejected (SQL Q06 returns 0 rows) |  | Not Executed | High | Boundary
TC_LOG_06 | Login and Logout | Blocked and inactive users cannot log in | Users with BLOCKED and INACTIVE status exist | karthik.rao@example.com (BLOCKED) ; anita.desai@example.com (INACTIVE), password Test@1234 | 1. Login as the blocked user 2. Login as the inactive user | Blocked: 'Account blocked, contact support'. Inactive: 'Account is inactive'. No session created |  | Not Executed | High | Negative
TC_LOG_07 | Login and Logout | Logout ends the session | User logged in | ravi.kumar@example.com | 1. Click Logout 2. Press browser Back button 3. Try to open the Order History URL directly | Redirected to Login; protected pages are not accessible after logout |  | Not Executed | High | Positive
TC_SRC_01 | Product Search | Search is case-insensitive | Home page open | headphones ; HEADPHONES ; HeadPhones | 1. Type each keyword in search box 2. Press Enter | Same result each time: SoundMax Wireless Headphones |  | Not Executed | High | Positive
TC_SRC_02 | Product Search | Search with no matching product | Home page open | xyzabc | 1. Search xyzabc | 'No products found' message with suggestion; no error page |  | Not Executed | Medium | Negative
TC_SRC_03 | Product Search | Search keyword length boundary | Home page open | 1 char: a ; 2 chars: so ; 100 chars of 'a' ; 101 chars of 'a' | 1. Search each value | 1 char: 'Enter at least 2 characters'; 2 chars returns SoundMax; 100 chars handled without error; 101 chars blocked or truncated (BR-05) |  | Not Executed | Medium | Boundary
TC_SRC_04 | Product Search | Unsafe text in the search box is treated as plain text | Home page open | ' OR 1=1 -- ; <script>alert(1)</script> | 1. Enter each text in search box 2. Press Enter | No script runs, no database error, not all products returned; shows 'No products found' |  | Not Executed | High | Negative
TC_CAT_01 | Categories and Product Details | Parent category shows sub-category products | Products exist under Electronics and Mobiles | Category: Electronics | 1. Open Electronics category | 6 products shown: Nova X5, Nova Lite, SoundMax, ChargePro, PowerMax Power Bank, Smart Watch Pro (compare with SQL Q10) |  | Not Executed | High | Positive
TC_CAT_02 | Categories and Product Details | Product details page shows correct data | Product Nova X5 exists | Nova X5 Smartphone 128GB | 1. Open the product from search or category 2. Compare page with DB | Name, description, price Rs.14,999, MRP Rs.17,999, '17% off', 'In Stock' shown correctly (SQL Q11) |  | Not Executed | High | Validation
TC_CAT_03 | Categories and Product Details | Out-of-stock product cannot be purchased | Smart Watch Pro stock = 0 | Smart Watch Pro | 1. Open Smart Watch Pro 2. Try to click Add to Cart | 'Out of Stock' label shown and Add to Cart is disabled (BR-07) |  | Not Executed | High | Negative
TC_CAT_04 | Categories and Product Details | Low-stock message | PowerMax Power Bank stock = 8 | PowerMax 10000mAh Power Bank | 1. Open the product page | 'Only 8 left' message displayed (SQL Q31 lists the product) |  | Not Executed | Medium | Positive
TC_CRT_01 | Shopping Cart | Add a product to cart | User logged in; empty cart | SoundMax Wireless Headphones (Rs.1,499) | 1. Open product page 2. Click Add to Cart 3. Open cart | Cart icon count 1; cart shows the item, quantity 1, price Rs.1,499. DB: 1 cart_items row (SQL Q12) |  | Not Executed | High | Positive
TC_CRT_02 | Shopping Cart | Adding the same product twice increases quantity | SoundMax already in cart | SoundMax Wireless Headphones | 1. Click Add to Cart again on the same product 2. Open cart | Single cart line with quantity 2; no duplicate line (DB unique rule cart_id + product_id) |  | Not Executed | High | Positive
TC_CRT_03 | Shopping Cart | Remove an item from the cart | Cart has 2 items | SoundMax and Steel Water Bottle | 1. Click Remove on SoundMax 2. Check cart totals | Item removed, totals recalculated, DB cart_items row deleted |  | Not Executed | High | Positive
TC_CRT_04 | Shopping Cart | Cart is saved after logout and login | Cart has 1 item | ravi.kumar@example.com | 1. Logout 2. Login again 3. Open cart | Same items and quantities still in cart |  | Not Executed | Medium | Positive
TC_CRT_05 | Shopping Cart | Empty cart behaviour | User logged in; cart empty | None | 1. Open cart page | 'Your cart is empty' message; Checkout button disabled |  | Not Executed | Medium | Negative
TC_QTY_01 | Quantity Updates | Increase quantity updates totals | Steel Water Bottle (Rs.349) in cart, qty 1 | Quantity 1 to 3 | 1. Change quantity to 3 2. Click Update | Line total Rs.1,047 and cart subtotal update immediately; DB quantity = 3 |  | Not Executed | High | Positive
TC_QTY_02 | Quantity Updates | Maximum quantity per order boundary | Steel Water Bottle in cart (stock 120) | Quantity 10 and 11 | 1. Set quantity to 10 and update 2. Set quantity to 11 and update | 10 accepted; 11 rejected with 'Maximum 10 per order' (BR-08) |  | Not Executed | High | Boundary
TC_QTY_03 | Quantity Updates | Minimum quantity boundary | Item in cart | Quantity 0 and -1 | 1. Enter 0 and update 2. Enter -1 and update | 0 asks to remove the item or is rejected; -1 rejected; cart never holds quantity below 1 |  | Not Executed | High | Boundary
TC_QTY_04 | Quantity Updates | Quantity cannot exceed available stock | PowerMax Power Bank stock = 8 | Quantity 8 and 9 | 1. Set quantity to 8 and update 2. Set quantity to 9 and update | 8 accepted; 9 rejected with 'Only 8 available' (SQL Q15 returns 0 rows) |  | Not Executed | High | Boundary
TC_QTY_05 | Quantity Updates | Invalid quantity input | Item in cart | abc ; 2.5 ; blank | 1. Enter each value in quantity box 2. Click Update | Each value rejected with a message; previous quantity retained |  | Not Executed | Medium | Validation
TC_CHK_01 | Checkout | Checkout requires login | User logged out; cart exists in guest session | None | 1. Click Checkout while logged out | User is redirected to Login; after login returns to checkout |  | Not Executed | High | Negative
TC_CHK_02 | Checkout | Price summary is calculated correctly | Cart: SoundMax x1 (1499) and ChargePro x2 (599) | Expected: subtotal 2697.00, shipping 0.00, GST 485.46, total 3182.46 | 1. Open Checkout 2. Compare each amount with expected values | All amounts match BR-09 to BR-11 exactly to 2 decimals |  | Not Executed | High | Functional
TC_CHK_03 | Checkout | Shipping fee boundary around Rs.500 | Notebook Pack (Rs.250) available | 1 unit: subtotal 250 ; 2 units: subtotal 500 | 1. Add 1 Notebook Pack and open Checkout 2. Change quantity to 2 and open Checkout | 1 unit: shipping 40, GST 45.00, total 335.00. 2 units: shipping 0, GST 90.00, total 590.00 (SQL Q18) |  | Not Executed | High | Boundary
TC_CHK_04 | Checkout | Price change after adding to cart | SoundMax in cart at Rs.1,499 | Change price in DB to 1399 for the test | 1. Update products.price via SQL 2. Refresh cart and open Checkout | Checkout uses the latest price and shows a notice about the price change (otherwise log defect; SQL Q14) |  | Not Executed | Medium | Functional
TC_ADR_01 | Address Validation | Add a valid new address | User logged in; at checkout | Name: Ravi Kumar, Phone: 9876543210, Line1: 12-4 Gandhi Road, City: Tirupati, State: Andhra Pradesh, Pincode: 517501 | 1. Click Add New Address 2. Enter data 3. Click Save | Address saved and selectable. DB: new addresses row linked to the customer |  | Not Executed | High | Positive
TC_ADR_02 | Address Validation | Mandatory address fields blank | Add Address form open | All fields empty | 1. Click Save with empty form | Errors for name, phone, line 1, city, state, pincode; address not saved |  | Not Executed | High | Negative
TC_ADR_03 | Address Validation | Pincode validation and boundary | Add Address form open | 12345 ; 1234567 ; 51750A ; 017501 ; 517501 | 1. Enter each pincode with other valid fields 2. Click Save | First four rejected (length, letters, leading 0); 517501 accepted (BR-12) |  | Not Executed | High | Boundary
TC_ADR_04 | Address Validation | Default address is pre-selected | Customer has 2 addresses, one default | ravi.kumar@example.com | 1. Go to Checkout 2. Check the selected address 3. Select the other address | Default (Home - Tirupati) is pre-selected; user can switch; final order uses the chosen address (SQL Q20) |  | Not Executed | Medium | Positive
TC_ADR_05 | Address Validation | User cannot use another customer's address | Two users exist; note an address_id of the other user | Address ID 3 belongs to Sneha; logged in as Ravi | 1. As Ravi, start checkout 2. Using browser dev tools or URL, change address ID to 3 3. Place order | Request rejected (error/403); order not created (SQL Q20 returns 0 rows) |  | Not Executed | High | Negative
TC_ORD_01 | Order Placement | Place an order successfully | Cart ready, address selected | SoundMax x1, ChargePro x2, UPI success@shopease | 1. Click Place Order 2. Pay using UPI success@shopease 3. Note the order number | Order confirmation page with order number. DB: orders, order_items and payments rows created; amounts correct (SQL Q16, Q22, Q24) |  | Not Executed | High | Positive
TC_ORD_02 | Order Placement | Double click on Place Order | Cart ready | Any cart | 1. Double-click the Place Order button quickly 2. Check Order History and DB | Only one order created; stock reduced only once |  | Not Executed | High | Negative
TC_ORD_03 | Order Placement | Refresh or Back after order placement | Order just placed | None | 1. Press F5 on confirmation page 2. Press Back and resubmit if possible | No second order is created; user sees the same confirmation or a safe page |  | Not Executed | Medium | Negative
TC_ORD_04 | Order Placement | Product becomes out of stock before payment | Item in cart; checkout page open | Set stock to 0 via SQL after opening checkout | 1. Open checkout 2. Run: UPDATE inventory SET quantity_available=0 for the product 3. Click Place Order | Order blocked with 'item out of stock' message; no order or payment row created |  | Not Executed | High | Negative
TC_PAY_01 | Payment Status Simulation | UPI payment success | Order ready for payment | UPI ID: success@shopease | 1. Choose UPI 2. Enter UPI ID and pay | Order CONFIRMED, payment SUCCESS, transaction id saved, paid_at filled (SQL Q28) |  | Not Executed | High | Positive
TC_PAY_02 | Payment Status Simulation | Card payment fails | Order ready for payment | Card number ending 0002 (simulated decline), valid expiry and CVV | 1. Choose Debit Card 2. Enter test card and pay | Message with option to retry; order PAYMENT_FAILED, payment FAILED with reason; stock NOT reduced (SQL Q27) |  | Not Executed | High | Negative
TC_PAY_03 | Payment Status Simulation | COD within the limit | Order total <= Rs.10,000 | Total Rs.1,353.46 | 1. Choose Cash on Delivery 2. Place order | Order PLACED, payment PENDING, transaction id NULL, stock reduced |  | Not Executed | Medium | Positive
TC_PAY_04 | Payment Status Simulation | COD not available above Rs.10,000 | Cart with Nova Lite (total 10,618.82) | Total Rs.10,618.82 | 1. Go to payment step | COD option disabled with a message; online methods available (SQL Q29 returns 0 rows) |  | Not Executed | Medium | Boundary
TC_PAY_05 | Payment Status Simulation | Invalid card details | Payment page open | Card 1234 5678 (too short) ; expiry 01/24 (expired) ; CVV 12 | 1. Enter each invalid detail 2. Click Pay | Field-level errors shown; no payment record created |  | Not Executed | Medium | Validation
TC_HIS_01 | Order History | Order history shows only own orders, newest first | User has 2 orders | ravi.kumar@example.com (orders SE-20261005-0006 and SE-20260915-0001) | 1. Login 2. Open My Orders | Only Ravi's 2 orders, newest first; matches SQL Q21 |  | Not Executed | High | Positive
TC_HIS_02 | Order History | Order details match the database | Order SE-20260915-0001 exists | Order SE-20260915-0001 | 1. Open the order details 2. Run SQL Q22 and compare each field | Items, quantity, price, shipping, GST, total, address and payment status all match |  | Not Executed | High | Validation
TC_HIS_03 | Order History | Cannot open another user's order by changing the URL | Logged in as Ravi | Order ID of Sneha (order 2) | 1. Open Ravi's order details 2. Change order ID in URL to 2 | Access denied or 'Order not found'; no data of another user is shown |  | Not Executed | High | Negative
TC_CAN_01 | Order Cancellation | Cancel a PLACED COD order | COD order in PLACED state; note stock before | Order SE-20261022-0003 | 1. Open order details 2. Click Cancel Order 3. Select reason and confirm | Order CANCELLED, cancelled_at set, payment CANCELLED, stock restored to previous value (SQL Q26, Q34) |  | Not Executed | High | Positive
TC_CAN_02 | Order Cancellation | Cancel a CONFIRMED prepaid order | UPI order in CONFIRMED state | Order SE-20261005-0006 | 1. Cancel the order with a reason | Order CANCELLED, payment REFUNDED, stock restored (SQL Q25, Q34) |  | Not Executed | High | Positive
TC_CAN_03 | Order Cancellation | Shipped and delivered orders cannot be cancelled | Orders in SHIPPED and DELIVERED state | SE-20260918-0002 (SHIPPED), SE-20260915-0001 (DELIVERED) | 1. Open each order 2. Look for the Cancel button 3. Try the cancel request directly via URL | Cancel option hidden or disabled; direct request rejected; status unchanged (BR-17) |  | Not Executed | High | Negative
TC_CAN_04 | Order Cancellation | Cancelling an already cancelled order | Order already CANCELLED | Order SE-20260925-0004 | 1. Open the order 2. Try to cancel again (repeat the request) | Rejected; stock restored only once and refund not duplicated |  | Not Executed | High | Negative
TC_CAN_05 | Order Cancellation | Cancellation reason is mandatory | PLACED order available | Reason: blank ; 'Other' with 201 characters | 1. Click Cancel Order 2. Submit without reason 3. Enter a 201-character reason | Blank reason rejected; reason over 200 characters rejected (column limit) |  | Not Executed | Low | Validation
TC_INV_01 | Inventory Validation | Stock reduces by the ordered quantity | Note stock of ChargePro (Q34 style check before) | ChargePro x2 via UPI | 1. Note quantity_available 2. Place and pay for the order 3. Check quantity_available again | Stock is exactly 2 lower than before |  | Not Executed | High | Positive
TC_INV_02 | Inventory Validation | Failed payment does not reduce stock | Note stock before | Card ending 0002 | 1. Note stock 2. Place an order and fail the payment 3. Check stock | Stock unchanged |  | Not Executed | High | Negative
TC_INV_03 | Inventory Validation | Last unit bought by two users at the same time | Product stock set to 1 | Two browsers: Ravi and Sneha | 1. Both users add the product 2. Both open checkout 3. Both click Place Order within seconds | Only one order succeeds; other user gets out-of-stock message; stock = 0 (never -1) (SQL Q32) |  | Not Executed | High | Negative
TC_INV_04 | Inventory Validation | Database blocks negative stock | DB access | UPDATE inventory SET quantity_available = -1 WHERE product_id = 3 | 1. Run the UPDATE in SQL client | MySQL rejects with CHECK constraint error chk_inventory_qty; data unchanged |  | Not Executed | Medium | Validation
TC_E2E_01 | End-to-End | Complete purchase with UPI | Anitha Rao registered (TC_REG_01) | Search: headphones; add SoundMax x1 and ChargePro x2; UPI success@shopease | 1. Login 2. Search headphones and add to cart 3. Add ChargePro x2 4. Checkout, select address 5. Pay with UPI 6. Open Order History 7. Run SQL Q22, Q16, Q24, Q34 | Order CONFIRMED; UI and DB agree on items, amounts, payment and stock; all CHECK queries return 0 rows |  | Not Executed | High | End-to-End
TC_E2E_02 | End-to-End | COD order then cancellation | Logged-in user with address | Steel Water Bottle x2, COD | 1. Add product x2 and place COD order 2. Verify PLACED/PENDING in DB 3. Cancel from Order History 4. Verify status and stock again | Order moves PLACED to CANCELLED; payment PENDING to CANCELLED; stock restored (SQL Q26, Q34) |  | Not Executed | High | End-to-End
TC_E2E_03 | End-to-End | Failed payment then successful retry | Logged-in user with address | Nova Lite x1; first card ending 0002, then UPI success@shopease | 1. Place order and fail card payment 2. Verify PAYMENT_FAILED and stock unchanged 3. Retry payment using UPI 4. Verify final state in DB | Single order ends CONFIRMED, payment SUCCESS with transaction id, stock reduced once, no duplicate order (SQL Q19, Q23, Q27) |  | Not Executed | High | End-to-End

## Defect Tracker
Bug ID | Type | Summary | Module | Linked TC | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Environment | Status | Reported By | Reported Date | SQL Evidence
BUG-S01 | SAMPLE | Cart subtotal wrong after increasing quantity | Quantity Updates | TC_QTY_01 | User logged in. Steel Water Bottle (Rs.349) in cart with quantity 1. | 1. Open the cart. 2. Change quantity of Steel Water Bottle from 1 to 3. 3. Click Update. 4. Read line total and cart subtotal. | Line total Rs.1,047.00 and cart subtotal Rs.1,047.00 (Q12 shows the same). | Line total shows Rs.1,047.00 but cart subtotal shows Rs.698.00 (quantity counted as 2). | High | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q12
BUG-S02 | SAMPLE | Stock not reduced after a successful order | Inventory Validation | TC_INV_01 | ChargePro stock noted as 200. User has valid cart and address. | 1. Note quantity_available of ChargePro (200). 2. Add ChargePro x2 to cart. 3. Place order and pay with UPI success@shopease. 4. Query inventory for the product. | quantity_available = 198 (reduced by 2, rule BR-16). | quantity_available is still 200. Order shows CONFIRMED. Risk of selling stock that does not exist. | High | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q34, Q32
BUG-S03 | SAMPLE | Checkout accepts pincode starting with 0 | Address Validation | TC_ADR_03 | User at checkout, Add Address form open. | 1. Enter valid name, phone, line 1, city, state. 2. Enter pincode 017501. 3. Click Save and continue to payment. | Error 'Enter a valid 6-digit pincode' and address not saved (BR-12). | Address saved and checkout continues. A row with pincode 017501 is stored. | Medium | Medium | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q39 (and review addresses table)
BUG-S04 | SAMPLE | Order shows CONFIRMED after card payment failed | Payment Status Simulation | TC_PAY_02 | Order ready for payment. Simulated card ending 0002 declines. | 1. Place an order and choose Debit Card. 2. Enter the declined test card with valid expiry and CVV. 3. Click Pay. 4. Open Order History and query the order. | Order status PAYMENT_FAILED, payment FAILED with a failure reason (BR-15). | Payment row is FAILED but order status is CONFIRMED, so the order would be shipped without payment. | Critical | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q27, Q28
BUG-S05 | SAMPLE | Double click on Place Order creates two orders | Order Placement | TC_ORD_02 | Cart ready, address selected. | 1. Open checkout. 2. Double-click Place Order quickly. 3. Open Order History and query orders for the customer. | Exactly one order is created. | Two orders with different order numbers and the same items are created; stock reduced twice. | High | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q46, Q30, Q34
BUG-S06 | SAMPLE | Cash on Delivery offered for order above Rs.10,000 | Payment Status Simulation | TC_PAY_04 | Cart contains Nova Lite Smartphone (total Rs.10,618.82). | 1. Open checkout with the cart. 2. Go to payment step. 3. Select Cash on Delivery and place the order. | COD option disabled with a message (BR-13). | COD is selectable and the order is placed with total 10,618.82. | High | Medium | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q29
BUG-S07 | SAMPLE | Account not blocked after 5 wrong passwords | Login and Logout | TC_LOG_05 | User priya.nair@example.com ACTIVE with 0 failed attempts. | 1. Enter a wrong password 5 times. 2. Enter the correct password Test@1234. | Account status BLOCKED after the 5th failure; correct password rejected (BR-04). | Status stays ACTIVE with failed_login_attempts 6; login with the correct password succeeds. | High | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q06
BUG-S08 | SAMPLE | Cancelled prepaid order is not refunded | Order Cancellation | TC_CAN_02 | UPI order in CONFIRMED state. | 1. Open the order in My Orders. 2. Click Cancel Order and choose a reason. 3. Query orders and payments for the order. | Order CANCELLED, payment REFUNDED (BR-17). | Order CANCELLED but payment still SUCCESS; no refund recorded. | Critical | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q25, Q40
BUG-S09 | SAMPLE | Shipping fee charged when subtotal is exactly Rs.500 | Checkout | TC_CHK_03 | Notebook Pack (Rs.250) available. | 1. Add 2 Notebook Packs (subtotal Rs.500). 2. Open checkout and read shipping fee. | Shipping Rs.0, GST 90.00, total 590.00 (BR-10: free from Rs.500). | Shipping Rs.40.00 and total 630.00 (rule applied as 'above 500'). | Medium | Medium | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | Q18, Q16
BUG-S10 | SAMPLE | Brand name misspelled in site header | Product Search | TC_SRC_01 | Home page open. | 1. Open the home page. 2. Read the header text. | Header shows 'ShopEase'. | Header shows 'ShopEse'. | Low | High | Simulated ShopEase test build v0.1 (fictional), Chrome latest, Windows 11, MySQL 8.0 database shopease_db | New (SAMPLE, not a real finding) | Sample | n/a | None (UI text only)
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL
ACTUAL

## RTM
Requirement ID | Test Case ID | Manual Test | Related Database Table | SQL Validation Query ID | Expected Database State | Execution Status
FR-01 (BR-01, BR-02, BR-03) | TC_REG_01 | Register with valid details | customers | Q01, Q02, Q03, Q44 | 1 new customers row; status ACTIVE; failed_login_attempts 0; password_hash is not plain text | Not Executed
FR-01 (BR-01) | TC_REG_02 | Register with an already registered email | customers | Q02 | Row count unchanged; no duplicate email | Not Executed
FR-01 (BR-01) | TC_REG_03 | Register with an already registered phone number | customers | Q03 | Row count unchanged; no duplicate phone | Not Executed
FR-01 (BR-01) | TC_REG_04 | Invalid email formats are rejected | customers | Q04 | No new row; no invalid email stored | Not Executed
FR-01 | TC_REG_05 | Mandatory fields left blank | customers | Q39, Q44 | No new row; no blank mandatory value stored | Not Executed
FR-01 (BR-02) | TC_REG_06 | Weak passwords are rejected (password policy) | customers | Q44 | No new row for each weak password | Not Executed
FR-01 (BR-02) | TC_REG_07 | Password length boundary values | customers | Q44 | New rows only for 8 and 20 character passwords; none for 7 and 21 | Not Executed
FR-01 (BR-02) | TC_REG_08 | Confirm password does not match | customers | Q44 | No new row | Not Executed
FR-01 (BR-01) | TC_REG_09 | Phone number validation | customers | Q39, Q44 | No new row; stored phones are all 10 digits starting 6-9 | Not Executed
FR-02 | TC_LOG_01 | Login with valid credentials | customers | Q06 | last_login_at updated; failed_login_attempts = 0 | Not Executed
FR-02 (BR-04) | TC_LOG_02 | Login with wrong password | customers | Q06 | failed_login_attempts increased by 1; status still ACTIVE | Not Executed
FR-02 | TC_LOG_03 | Login with unregistered email | customers | Q44 | No change in any table | Not Executed
FR-02 | TC_LOG_04 | Login with blank fields | customers | Q06 | No change in failed_login_attempts | Not Executed
FR-02 (BR-04) | TC_LOG_05 | Account locks after 5 wrong passwords (boundary 4 vs 5) | customers | Q06 | After 4 failures status ACTIVE; after the 5th status BLOCKED | Not Executed
FR-02 (BR-04) | TC_LOG_06 | Blocked and inactive users cannot log in | customers | Q06 | Status remains BLOCKED / INACTIVE; last_login_at unchanged | Not Executed
FR-02 | TC_LOG_07 | Logout ends the session | None (session only) | - | No database change; verify by UI | Not Executed
FR-03 (BR-05) | TC_SRC_01 | Search is case-insensitive | products | Q10 | Read-only; result matches products with name containing 'headphones' | Not Executed
FR-03 | TC_SRC_02 | Search with no matching product | products | - | No database change | Not Executed
FR-03 (BR-05) | TC_SRC_03 | Search keyword length boundary | products | - | No database change | Not Executed
FR-03 | TC_SRC_04 | Unsafe text in the search box is treated as plain text | all tables | Q44 | Row counts of all tables unchanged (no injection effect) | Not Executed
FR-04 (BR-06) | TC_CAT_01 | Parent category shows sub-category products | categories, products | Q10 | UI count for Electronics equals Q10 (6 on sample data) | Not Executed
FR-04 | TC_CAT_02 | Product details page shows correct data | products | Q07, Q08, Q09, Q11 | UI price, MRP and discount % equal database values | Not Executed
FR-04 (BR-07) | TC_CAT_03 | Out-of-stock product cannot be purchased | products, inventory | Q31 | Smart Watch Pro quantity_available = 0 | Not Executed
FR-04 (BR-07) | TC_CAT_04 | Low-stock message | products, inventory | Q31 | PowerMax Power Bank quantity_available = 8 (<= reorder level) | Not Executed
FR-05 | TC_CRT_01 | Add a product to cart | carts, cart_items | Q12, Q14 | 1 cart_items row for the product, quantity 1, unit_price 1499.00 | Not Executed
FR-05 | TC_CRT_02 | Adding the same product twice increases quantity | cart_items | Q12 | Still one cart_items row for the product, quantity 2 | Not Executed
FR-05 | TC_CRT_03 | Remove an item from the cart | cart_items | Q12 | Removed product row is gone; remaining total matches the UI | Not Executed
FR-05 | TC_CRT_04 | Cart is saved after logout and login | carts, cart_items | Q12, Q13 | Same cart_items rows; one ACTIVE cart per customer | Not Executed
FR-05 | TC_CRT_05 | Empty cart behaviour | carts, cart_items | Q12 | Cart has no cart_items rows | Not Executed
FR-06 | TC_QTY_01 | Increase quantity updates totals | cart_items | Q12 | quantity = 3; cart value updated | Not Executed
FR-06 (BR-08) | TC_QTY_02 | Maximum quantity per order boundary | cart_items, products | Q15 | quantity = 10 allowed; 11 never stored | Not Executed
FR-06 (BR-08) | TC_QTY_03 | Minimum quantity boundary | cart_items | Q15 | No row with quantity below 1 | Not Executed
FR-06 (BR-08) | TC_QTY_04 | Quantity cannot exceed available stock | cart_items, inventory | Q15 | quantity 8 stored; 9 never stored | Not Executed
FR-06 | TC_QTY_05 | Invalid quantity input | cart_items | Q15 | Quantity unchanged after invalid input | Not Executed
FR-07 | TC_CHK_01 | Checkout requires login | None (session only) | - | No order or cart change | Not Executed
FR-07 (BR-09, BR-10, BR-11) | TC_CHK_02 | Price summary is calculated correctly | carts, cart_items | Q12, Q16, Q17 | Cart value 2697.00 equals checkout subtotal; later order total equals 3182.46 | Not Executed
FR-07 (BR-10) | TC_CHK_03 | Shipping fee boundary around Rs.500 | orders | Q18 | Order of 250 has shipping_fee 40; order of 500 has shipping_fee 0 | Not Executed
FR-07 | TC_CHK_04 | Price change after adding to cart | cart_items, products | Q14 | Checkout uses products.price; Q14 shows no stale price after refresh | Not Executed
FR-08 (BR-12) | TC_ADR_01 | Add a valid new address | addresses | Q47, Q39 | 1 new addresses row linked to the logged-in customer | Not Executed
FR-08 | TC_ADR_02 | Mandatory address fields blank | addresses | Q39 | No new row | Not Executed
FR-08 (BR-12) | TC_ADR_03 | Pincode validation and boundary | addresses | Q39 | Only the 517501 address is stored | Not Executed
FR-08 | TC_ADR_04 | Default address is pre-selected | addresses, orders | Q05, Q20 | Exactly one default address per customer; order uses chosen address | Not Executed
FR-08 (BR-18) | TC_ADR_05 | User cannot use another customer's address | orders, addresses | Q20 | No order exists whose address belongs to another customer | Not Executed
FR-09 | TC_ORD_01 | Place an order successfully | orders, order_items, payments, inventory | Q16, Q19, Q22, Q23, Q24, Q34 | 1 order, correct items, 1 payment with equal amount, stock reduced by ordered quantity | Not Executed
FR-09 | TC_ORD_02 | Double click on Place Order | orders, order_items, payments | Q30, Q46, Q23 | Exactly one new order; no duplicate lines or transactions; stock reduced once | Not Executed
FR-09 | TC_ORD_03 | Refresh or Back after order placement | orders | Q23, Q46 | Order count unchanged after refresh/back | Not Executed
FR-09 (BR-16) | TC_ORD_04 | Product becomes out of stock before payment | inventory, orders | Q32, Q44 | No new order or payment row; stock stays 0, not negative | Not Executed
FR-10 (BR-15) | TC_PAY_01 | UPI payment success | orders, payments | Q28, Q41 | Order CONFIRMED; payment SUCCESS with transaction_id and paid_at | Not Executed
FR-10 (BR-15, BR-16) | TC_PAY_02 | Card payment fails | orders, payments, inventory | Q27, Q41, Q34 | Order PAYMENT_FAILED; payment FAILED with reason; stock unchanged | Not Executed
FR-10 (BR-13, BR-15) | TC_PAY_03 | COD within the limit | orders, payments, inventory | Q29, Q42 | Order PLACED; payment PENDING; transaction_id NULL; stock reduced | Not Executed
FR-10 (BR-13) | TC_PAY_04 | COD not available above Rs.10,000 | orders | Q29 | No COD order above 10000 | Not Executed
FR-10 | TC_PAY_05 | Invalid card details | payments | Q23 | No payment row created | Not Executed
FR-11 (BR-18) | TC_HIS_01 | Order history shows only own orders, newest first | orders | Q21 | UI list equals the Q21 result for that customer | Not Executed
FR-11 | TC_HIS_02 | Order details match the database | orders, order_items, products, addresses, payments | Q22 | Every UI field equals the Q22 row values | Not Executed
FR-11 (BR-18) | TC_HIS_03 | Cannot open another user's order by changing the URL | orders | Q20 | No data change; access denied for another customer's order | Not Executed
FR-12 (BR-17) | TC_CAN_01 | Cancel a PLACED COD order | orders, payments, inventory | Q26, Q34, Q40 | Order CANCELLED with cancelled_at and reason; payment CANCELLED; stock restored | Not Executed
FR-12 (BR-17) | TC_CAN_02 | Cancel a CONFIRMED prepaid order | orders, payments, inventory | Q25, Q34, Q40 | Order CANCELLED; payment REFUNDED; stock restored | Not Executed
FR-12 (BR-17) | TC_CAN_03 | Shipped and delivered orders cannot be cancelled | orders | Q40 | SHIPPED and DELIVERED orders keep status; cancelled_at stays NULL | Not Executed
FR-12 (BR-17) | TC_CAN_04 | Cancelling an already cancelled order | orders, payments, inventory | Q25, Q34 | Stock restored once only; payment not refunded twice | Not Executed
FR-12 | TC_CAN_05 | Cancellation reason is mandatory | orders | Q40 | No cancellation stored without a reason | Not Executed
FR-13 (BR-16) | TC_INV_01 | Stock reduces by the ordered quantity | inventory, order_items | Q34, Q32 | quantity_available reduced by exactly the ordered quantity (2) | Not Executed
FR-13 (BR-16) | TC_INV_02 | Failed payment does not reduce stock | inventory, orders | Q34, Q27 | Stock equals value noted before the test | Not Executed
FR-13 (BR-16) | TC_INV_03 | Last unit bought by two users at the same time | inventory, orders | Q32 | One new order only; stock = 0 and never negative | Not Executed
FR-13 | TC_INV_04 | Database blocks negative stock | inventory | Q32 | MySQL rejects the UPDATE; stock unchanged | Not Executed
FR-01 to FR-11 | TC_E2E_01 | Complete purchase with UPI | customers, carts, cart_items, orders, order_items, payments, inventory | Q01, Q16, Q19, Q22, Q23, Q24, Q28, Q34, Q43, Q45, Q48 | Order CONFIRMED; items, amounts, payment and stock all consistent; all CHECK queries return 0 rows | Not Executed
FR-09, FR-10, FR-12, FR-13 | TC_E2E_02 | COD order then cancellation | orders, payments, inventory | Q26, Q34, Q40 | PLACED/PENDING then CANCELLED/CANCELLED; stock back to the start value | Not Executed
FR-09, FR-10, FR-13 | TC_E2E_03 | Failed payment then successful retry | orders, payments, inventory | Q19, Q23, Q27, Q28, Q34 | One order ends CONFIRMED; one payment SUCCESS; stock reduced once | Not Executed